## Slide 1: Calendar Overview – Phase I – REVISED April 2019
Sept 2017
Sept 2018
Initial
Drafting
First drafts developed in WG
Sept to late June 2018
Draft update post-Pescara by WG Leads
Stage 2
Working Groups and Participants’ Work
Work by Steering Committee
Stage 1
Face to face meeting Pescara
12-14 Sept. 2018
Stage 3
12 months
9 months
20 months period
Consolidating Draft
Create V1 draft & submit for internal revision
Face to face meeting in Paris
24-26 April 2019
4 months
Stage 5
Formatting, UN Env review, Publication
March-April 2020
5 months
Sept 2019
Jan 2019
Draft Update by SC members
Create V2 draft
Draft Update by SC members
Create V3 draft
Summer
2019
Stage 4
Draft Update by SC members
Create V4 draft
Dec-March
2019-2020
4 months
Jan 2020
May 2020
Informal Consultation with external Stakeholders by SC members
Jan – April 2019
Send out V2 draft to participants
With instructions on how to provide feedback
mid-Feb 2019
Send out V3 draft to participants & UN peer review
Early Sept2019
Webinar on launch for public consultation
October 2019
Call for expressions of interest for the Pilots
June 2019 & end of August 2019
Kick off for launching pilots (webinar)
Nov
2019
Comment period on V3
Sept-Nov 2019
Webinar on outcome Paris
May 2019
Check on acceptance
March 2020
Notes: Last update: Nov 14, 2018 (SRG)

## Slide 2
2nd Webinar for pilots
Feb 2020
Calendar Overview – Phase II – REVISED April 2019
Piloting stage starts
Jan 2020
Regular follow-up meetings for support
Start March 2020
Steering Committee work
Road Testing
Stage 2
In-person meeting for pilots
June 2020 at SLCA 2020
Intermediate pilot reports
June/July 2020
Internal review of draft pilot reports
Start Nov 2020
S-LCA and SOLCA case studies & development of a report
Start Nov 2020
Final pilot reports
Feb 2021
Formatting, UN Env review, Publication
June-July 2021
Dissemination phase
Fall 2021
Stage 3
June 2019
26 months period
Aug 2020
Jan 2020
Jan 2021
August 2021
June 2020
Call for expressions of interest for the Pilots
June 2019 & end of August 2019
Kick off for launching pilots (1st webinar)
Nov
2019
Draft pilot reports
Nov 2020
Consolidated final pilot report with lessons learned
May 2021
Stage 1
6 months
7 months
13 months